## Functional
Project Name: | Panda Mall
Superviser Name: | Mr. Razi-uddin
Deliverable: | Project Status
ID | Functional Requirement | Priority | Status Completed | Deadline (week no of semester) | Resource
1 | User can login using his/her credentials | Medium | 0% | Week 11 | Tayyab Waseem, M.Zain, Asjad I.
2 | User can create a new account by proivding required information | Medium | 0% | Week 11 | Tayyab Waseem, M.Zain, Asjad I.
3 | User can reset password via email | Medium | 0% | Week 11 | Tayyab Waseem, M.Zain, Asjad I.
4 | User can logout | Medium | 80% | Week 11 | Tayyab Waseem, M.Zain, Asjad I.
5 | User can edit profile | Medium | 80% | Week 11 | Tayyab Waseem, M.Zain
6 | User can view products based on his/her profile | High | 90% | Week 7 | Tayyab Waseem, M.Zain
7 | User can filter out products based on Type | High | 70% | Week 7 | Tayyab Waseem, M.Zain
8 | User can filter out products based on Sizes | High | 70% | Week 7 | Tayyab Waseem, M.Zain
9 | User can filter out products based on Colors | High | 100% | Week 7 | Tayyab Waseem, M.Zain
10 | User can filter out products based on Waists | High | 70% | Week 7 | Tayyab Waseem, M.Zain
11 | User can filter out products based on Price Range | High | 70% | Week 7 | Tayyab Waseem, M.Zain
12 | User can filter out products based on Discount Factor | High | 70% | Week 7 | Tayyab Waseem, M.Zain
13 | User can filter out products based on Brands | High | 100% | Week 7 | Tayyab Waseem, M.Zain
14 | User can view product details | Medium | 100% | Week 5 | Tayyab Waseem, M.Zain
15 | User can buy product from brands official page | Low | 100% | Week 7 | Tayyab Waseem, M.Zain
16 | User can add products to favourites | Medium | 50% | Week 11 | Tayyab Waseem, M.Zain
17 | User can give feedback on the product bought | Low | 10% | Week 11 | Tayyab Waseem, M.Zain
18 | Stores can add products | High | 100% | Week 4 | Asjad Iftikhar
19 | Stores can update products | High | 100% | Week 4 | Asjad Iftikhar
20 | Stores can view products | High | 100% | N/A | Asjad Iftikhar
21 | Stores can remove products | High | 100% | N/A | Asjad Iftikhar
22 | Stores can view dashboard | Low | 60% | Week 5 | Asjad Iftikhar
23 | Administrator can approve/reject products | High | 40% | Week 7 | Asjad Iftikhar
24 | Administrator can update products | Medium | 100% | Week 7 | Asjad Iftikhar
25 | Administrator can view products | Low | 100% | Week 7 | Asjad Iftikhar

## Non-Functional
Project Name: | Panda Mall
Superviser Name: | Mr. Razi-uddin
Deliverable: | Project Status
ID | Non-Functional Requirement | Priority | Status Completed | Deadline (week no of semester) | Resource
1 | Availability - Available 160 hours a week | High | 0% | Week 11 | Asjad iftikhar, Tayyab Waseem, M.Zain
2 | Usability - intuitive design | High | 100% | N/A | Asjad iftikhar, Tayyab Waseem, M.Zain
3 | Reliability - get results within 3 seconds | Medium | 0% |  | Tayyab Waseem, M.Zain
4 | Scalability - at most 100 users | Medium | 0% | Week 11 | Asjad iftikhar, Tayyab Waseem, M.Zain
5 | Data Integrity - protection against tampering | High | 100% | Week 5 | Asjad iftikhar, Tayyab Waseem, M.Zain
6 | Performance - Pagination to improve load times | High | 0% |  | Tayyab Waseem, M.Zain

## Instructions
Instructions For Completing This Document
Complete the Project Name and Superviser Name
ID: A unique ID number used to identify the requirement
Functional Requirement: This column should be populated with a description of the functional requirement. | Non-Functional Requirement: This column should be populated with a description of the non-functional requirement.
Status: This column should be populated with the current status of the functional requirement.
Deadline: This column should be populated for the requirements whose status is incomplete.
Resource: Team member who completed/will complete the requirement implmentation.