## Functional
Project Name: | Panda Mall
Superviser Name: | Mr. Razi-uddin
Deliverable: | Project Status
ID | Functional Requirement | Priority | Status Completed | Deadline (week no of semester) | Resource
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18 | Stores can add products | High | 70% | Week 4 | Asjad Iftikhar
19 | Stores can update products | High | 70% | Week 4 | Asjad Iftikhar
20 | Stores can view products | High | 100% | N/A | Asjad Iftikhar
21 | Stores can remove products | High | 100% | N/A | Asjad Iftikhar
22 | Stores can view dashboard | Low | 30% | Week 5 | Asjad Iftikhar
23 | Administrator can approve/reject products | High | 0% | Week 7 | Asjad Iftikhar
24 | Administrator can update products | Medium | 0% | Week 7 | Asjad Iftikhar
25 | Administrator can view products | Low | 0% | Week 7 | Asjad Iftikhar

## Non-Functional
Project Name: | Panda Mall
Superviser Name: | Mr. Razi-uddin
Deliverable: | Project Status
ID | Non-Functional Requirement | Priority | Status Completed | Deadline (week no of semester) | Resource
1 | Availability - Available 160 hours a week | High | 0% | Week 11 | Asjad iftikhar, Tayyab Waseem, M.Zain
2 | Usability - intuitive design | High | 100% | N/A | Asjad iftikhar, Tayyab Waseem, M.Zain
3 | Reliability - get results within 3 seconds | Medium | 0% |  | Tayyab Waseem, M.Zain
4 | Scalability - at most 100 users | Medium | 0% | Week 11 | Asjad iftikhar, Tayyab Waseem, M.Zain
5 | Data Integrity - protection against tampering | High | 0% | Week 5 | Asjad iftikhar, Tayyab Waseem, M.Zain
6 | Performance - Pagination to improve load times | High | 0% |  | Tayyab Waseem, M.Zain

## Instructions
Instructions For Completing This Document
Complete the Project Name and Superviser Name
ID: A unique ID number used to identify the requirement
Functional Requirement: This column should be populated with a description of the functional requirement. | Non-Functional Requirement: This column should be populated with a description of the non-functional requirement.
Status: This column should be populated with the current status of the functional requirement.
Deadline: This column should be populated for the requirements whose status is incomplete.
Resource: Team member who completed/will complete the requirement implmentation.